## NAMS DevOps Plan
NAMS DevOps Plan
Instruction: Mark with an X in the time line when the deadline is set for each deliverable
[9 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | june |  |  | july |  |  |  | august |  |  |  |  | september |  |  |  | october |  |  |  | november |  |  |  |  | december |  |  |  | january/18 |  |  |  |  | february/18 |  |  |  | march/18 |  |  |  | april/18
[9 empty] | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
ID | X,X Milestones | Resp. | Status | Base | % spent | Base | % compl. | Corrective actions | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Collaboration tool: evaluation and incorporation | Fabio |  | 100% | 0% | 100% | 0% | [40 empty] | x | x
1.1 | Decide which tool will be used (Slack) - used by VGT | Lead |  | 100% | 0% | 100% | 0% | [40 empty] | x
1.2 | Configure it for the team | Fabio |  | 100% | 0% | 100% | 0% | [41 empty] | x
1.3 | Demonstrate to the team how and why to use it | Fabio |  | 100% | 0% | 100% | 0% | [41 empty] | x
1.4 | Assume it as a standard tool to be used in all team comunications | Lead |  | 100% | 0% | 100% | 0% | [41 empty] | x
2 | Continuous Integration (CI) | Fabio/Kostas/Seilor |  | 100% | 0% | 100% | 0% | [41 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x
2.1 | Configure Builds to have CI build |  |  | 100% | 0% | 100% | 0% | [41 empty] | x
2.2 | Define how NAMS can work in a CI mode |  |  | 100% | 0% | 100% | 0% | [41 empty] | x
2.3 | Configuration must be automated when possible |  |  | 100% | 0% | 100% | 0% | [42 empty] | x | x | x | x | x | x | x | x | x | x | x | x
2.4 | Add SonarQube analisys |  |  | 100% | 0% | 100% | 0% | [42 empty] | x
3 | Robot Framework Implementation | Marlon |  | 100% | 0% | 100% | 0% | [40 empty] | x
3.1 | Create first smoke test |  |  | 100% | 0% | 100% | 0%
3.2 | Train more people to create tests |  |  | 100% | 0% | 100% | 0%
3.3 | Run it after deploymnets (recurrent task) |  |  | 100% | 0% | 100% | 0%
3.4 |  |  |  | 100% | 0% | 100% | 0%
4 | Braching and Merging | Fabio/Dewes |  | 100% | 0% | 100% | 0% | [40 empty] | x | x | x | x
4.1 | Evaluate the current model |  |  | 100% | 0% | 100% | 0% | [40 empty] | x
4.2 | Check the need and will to use git repos |  |  | 100% | 0% | 100% | 0% | [40 empty] | x
4.3 | Restructure what is needed |  |  | 100% | 0% | 100% | 0% | [40 empty] | x | x | x | x
4.4 |  |  |  | 100% | 0% | 100% | 0%
5 | General items |  |  | 100% | 0% | 100% | 0% | [40 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x
5.1 | Find someone from HCL to answer questions about the infrastructure |  |  | 100% | 0% | 100% | 0%
5.2 | Cloud: How, When, Where? |  |  | 100% | 0% | 100% | 0%
5.3 | Define what is "a Release" -> New model |  |  | 100% | 0% | 100% | 0%
5.4 | Windows Docker images investigation |  |  | 100% | 0% | 100% | 0% | [40 empty] | x
5.5 | Answer questions about Leadership | Annete |  | 100% | 0% | 100% | 0% | [40 empty] | x
6 | Continuous deployment |  |  | 100% | 0% | 100% | 0% | [53 empty] | x | x | x | x | x | x | x | x
6.1 | Prepare the CD standard |  |  | 100% | 0% | 100% | 0%
6.4 | Commit/Deploy/Test |  |  | 100% | 0% | 100% | 0%

## pilot master plan (draft)
Master Plan pilot XXX
Instruction: Mark with an X in the time line when the deadline is set for each deliverable
[9 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | june |  |  | july |  |  |  | august |  |  |  |  | september |  |  |  | october |  |  |  | november |  |  |  |  | december |  |  |  | january/18 |  |  |  |  | february/18 |  |  |  | march/18 |  |  |  | april/18
[9 empty] | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
ID | X,X Milestones | Resp. | Status | Base | % spent | Base | % compl. | Corrective actions | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Select acceptance test framework | Lead |  | 100% | 35% | 100% | 25%
1.1 | action 1 |  |  | 100% | 45% | 100% | 40%
1.2 | action 2 |  |  | 100% | 80% | 100% | 75%
1.3 | ... |  |  | 100% | 55% | 100% | 60%
1.4 |  |  |  | 100% | 40% | 100% | 0%
1.5 |  |  |  | 100% | 20% | 100% | 0%
1.6 |  |  |  | 100% | 10% | 100% | 0%
1.7 |  |  |  | 100% | 0% | 100% | 0%
1.8
2 | Automated acceptance tests | Lead |  | 100% | 0% | 100% | 0%
2.1 | ... |  |  | 100% | 0% | 100% | 0%
2.2 | ... |  |  | 100% | 0% | 100% | 0%
2.3 | ... |  |  | 100% | 0% | 100% | 0%
2.4 |  |  |  | 100% | 0% | 100% | 0%
3 | [recommendation 3] | Lead |  | 100% | 0% | 100% | 0%
3.1 | ... |  |  | 100% | 0% | 100% | 0%
3.2 | ... |  |  | 100% | 0% | 100% | 0%
3.3 |  |  |  | 100% | 0% | 100% | 0%
3.4 |  |  |  | 100% | 0% | 100% | 0%
4 | [recommendation 4] | Lead |  | 100% | 0% | 100% | 0%
4.1 | ... |  |  | 100% | 0% | 100% | 0%
4.2 | ... |  |  | 100% | 0% | 100% | 0%
4.3 |  |  |  | 100% | 0% | 100% | 0%
4.4 |  |  |  | 100% | 0% | 100% | 0%
5 | [recommendation 5] | Lead |  | 100% | 0% | 100% | 0%
5.1 | ... |  |  | 100% | 0% | 100% | 0%
5.2 | ... |  |  | 100% | 0% | 100% | 0%
5.3 |  |  |  | 100% | 0% | 100% | 0%
5.4 |  |  |  | 100% | 0% | 100% | 0%

## Sample_Suggesstions
Define mission | Select a timespan and work together to define a clear mission for PROMPT.
B | Mission is crucial for Team’s motivation. It is essential to know what a Team is aiming for in order to unify goals and work towards a common mission
Evaluate acceptance test framework | Evaluate the current test automation framework. Test cases and test report should be clear enough for business people to read and comprehend.
B | Creating automatic acceptance tests is a Team effort. Taking a moment to evaluate and deciding the tools together is the first step in getting everyone on board on test automation. Study whether you can make use of the current test cases, if you choose to change the test framework.
Automated acceptance tests | Work together as a team to implement automated acceptance tests. Start with critical business flows. Reuse the current automated tests and HP Quality Center cases to build a core for automated acceptance tests. Abandon HP Quality Center. To unify versioning, make sure acceptance tests are in the same Git repository with code.
B | Currently it takes some effort to get an overall picture of PROMPT quality. Furthermore, development and testing are conducted sequentially and developers need to wait for a long time before they get a verification of produced quality. Automatic acceptance tests allow testers and developers to put effort on the same feature more in parallel and reduce the regression feedback cycle for developers. Automatic acceptance tests’ reports also act as a real time quality status for the product. Manual testing also prevents effective use of continuous integration, since testing takes days or even weeks and requires code version to be frozen for this period. With automatic tests every new software version can be deployed and tested automatically and in reduced time. Cost per testing iteration goes down compared to manual testing.
Increase coverage of unit tests | Testing algorithms and different configuration combinations is not feasible in acceptance tests. Increase unit test level to cover all functions with important business logic in the application. Start using SonarQube to systematically track unit test coverage.
B | Good unit test coverage gives the Team confidence to proceed post haste. Unit tests that are executed every time a code commit is done ensure that the low level code components work as expected and don’t produce surprising results. Unit tests are also cheap to run and catching bugs this early means that they are easier and cheaper to fix compared to later stages of the project.
Definition of Done | Remove ready for testing column and start implementing testing along with code. When defining subtasks for a story, define also subtasks for unit and acceptance test implementation. Define and document Definition of Done so that it includes also test creation.
B | Having a written Definition of Done brings clarity into software delivery process. If Definition of Done is not written anywhere, people may have different opinions or perceptions of whether or not a task is done. Including test case development in Definition of Done is the first step towards a less siloed team culture, where testers and developers mostly work together on features instead of taking turns on them.
Git workflow | Define and document a proper Git branching strategy to support new Definition of Done and proper workflow. Start working together as development and testing in feature branches until the feature and both unit and acceptance tests are implemented and only then merge feature to master. Apply a code review process to merging into master.
B | Git workflow has a big impact on software production process. Reshaping your git workflow allows you to support the new Definition of Done. Workflow also defines what a change is. If you define a change to be every commit, then processing every change in CI can be quite chaotic. Defining a change to be every feature merge to master drastically reduces the pace of continuous integration so that building, deploying and testing every change becomes feasible. Furthermore, it is the optimal moment for code reviews, if you ever wish to apply review process to every change.
Continuous integration plan | Trigger unit tests, build and deployment to test environment on every merge to master. Evolve the process later by triggering, for example, smoke tests for each push to test branches as well. Trigger automatic acceptance tests on every deployment to verify quality of new and existing features
B | With a true Continuous integration environment you gain the possibility to see the basic overall status of the software after someone has done a new software update. The new software has been verified that it’s buildable, basic tests have verified that it’s not broken, the software has been updated to a dedicated test environment and automated acceptance tests verify that the software’s quality hasn’t decreased
Evaluate current environments | Evaluate whether all environments are needed.Take into account whether some environments could be removed while utilizing the CI-pipeline efficiently and business side would test from one QA-environment
B | Removing unused environment will provide cost savings. As well this task will inform whether all processes are efficient or not, for example, business’s testing activities
Evaluate DB needs | Evaluate the current DB usage, take into account all used environments and future development plans. Study whether you could have an archive DB in use.
B | The current DB is quite large and it isn’t fully supported in all of the environment being used by the Team. After evaluating the DB needs the Team should know which DB they could utilize now and in the future to support all different activities.
Implement DB changes | Based on the previous step implement the changes that help the Team to perform its tasks from development to production. End users shouldn’t see a behaviour change caused by this change
B | The development and test team should be able to perform their duties without problems. The DB should support all testing activities, for example, performance testing with large test data. The DBs should be identical in all environments.
Propose new release process | Whenever new EPICs are completed and tests pass in test environment, deploy to QA and let business know you’re ready for release any time they want. Make acceptance test results available for everyone.
B | With the renewed release process the Team has the possibility to provide business updated application software after each EPIC has been finalized. The software quality has been verified with acceptance tests in the Test environment and exactly same application software version has been provided to the QA environment for the business for their review. Additionally business has the possibility and power to accept the new application software and get it released to the Production environment.
Componentization plan | Establish a common understanding of individually deployable components in PROMPT. Make sure no components are both services and clients
B | In order to proceed with the transformation to a microservice model the application’s components have to be studied and their individual role understood. Each component has a dedicated role, some are services and some are client, but none should be both.
Componentization execution | Conduct componentization. Refactor PROMPT into separately deployable components
B | Components enable easier management of the software. Logic is compartmentalized into logical entities and managed independently. Changes to production are lighter when components can be changed independently instead of a single monolithic software. Ripple effect of changes to other components is reduced considerably
Transition into OpenShift | Put components into Docker containers and deploy them to OpenShift when it’s officially production ready.
B | Put components into Docker containers and deploy them to OpenShift when it’s officially production ready. Transition into OpenShift supports proper separation of responsibilities. Supplier should be responsible of the platform and you should be responsible of deployment and uptime of your application. End-to-end responsibility is in the core of Devops teams and gives you the freedom of deploying new versions of components in a reliable manner without any need for supplier intervention. OpenShift is built to support this, where supplier runs the platform and you deploy your application via an automatic interface. Also, this will probably cause heavy cost reduction in operations.
Build container monitoring | Start monitoring your containers and take end-to-end product responsibility. Use a modern container monitoring tool, for example, Prometheus
B | Even though OpenShift can automatically relaunch your application when it fails, monitoring and alerting are essential for you to know that something is wrong so that you can start investigating the root cause of issues and apply fixes to your application.

## XE_BPM
Highlevel -KPI
Reduce Lead-time
Increase Quality
Team | Metrics category | Metrics | Description | Desired update frequency | Currently available? | Current tool to display metrics | Target tool to display metrics | Comments
PROMPT | Delivery precision | Uptime | Uptime of each environment: Test, Dev, QA, Prod | according to retrospectives | No | SNOW | tbd | Uptime data available for Prod.
PROMPT | Delivery precision | Incident count | Incident count in each environment: Test, Dev, QA, Prod | according to retrospectives | No | SNOW | tbd
PROMPT | Delivery precision | Mean Time To Recover | Mean Time To Recover in each environment: Test, Dev, QA, Prod | according to retrospectives | No | SNOW | tbd
PROMPT | Test automation | Test automation status | Number of OK tests and number of NOK tests | according to retrospectives | Yes | Selenium | tbd
PROMPT | Deployment Frequency | Deployment Frequency | Deployment Frequency in each environment: Test, Dev, QA, Prod | according to retrospectives | No | none | tbd
PROMPT | Change lead time | tbd | tbd | according to retrospectives | No | none | tbd
PROMPT | Quality of change | Deployment effectiveness | tbd | according to retrospectives | No | JIRA, Jenkins | tbd
PROMPT | ? | Technical debt | Technical debt |  | Yes | SONAR QUBE | tbd
Suggesstions
| What is currently followed - list down the bottneck items -Ofcourse Eficode final report will be referred soon |  | Define mission | Clear mission but not especially motivating
| What improvements can be brought for the business |  | Evaluate acceptance test framework
| How the business is going to be befinit becouse of DevOps process |  | Automated acceptance tests
Increase coverage of unit tests
Definition of Done
Git workflow
Evaluate current environments
Evaluate DB needs
Implement DB changes
Propose new release process
Componentization plan
Componentization execution
Transition into OpenShift
Build container monitoring
| Metrics category | Metrics | Description | Desired update frequency | Currently available? | Current tool to display metrics | Target tool to display metrics | Comments
| Delivery precision | Uptime | Uptime of each environment: Test, Dev, QA, Prod | according to retrospectives | No | SNOW | tbd | Uptime data available for Prod.
| Delivery precision | Incident count | Incident count in each environment: Test, Dev, QA, Prod | according to retrospectives | No | SNOW | tbd
| Delivery precision | Mean Time To Recover | Mean Time To Recover in each environment: Test, Dev, QA, Prod | according to retrospectives | No | SNOW | tbd
| Test automation | Test automation status | Number of OK tests and number of NOK tests | according to retrospectives | Yes | Selenium | tbd
| Deployment Frequency | Deployment Frequency | Deployment Frequency in each environment: Test, Dev, QA, Prod | according to retrospectives | No | none | tbd
| Change lead time | tbd | tbd | according to retrospectives | No | none | tbd
| Quality of change | Deployment effectiveness | tbd | according to retrospectives | No | JIRA, Jenkins | tbd
| ? | Technical debt | Technical debt |  | Yes | SONAR QUBE | tbd
Incident count
|  | improvement | defects can be reduced
no. of defects are registered
|  |  | Teamplace for estimation | Assigned
Analuze
cost estimation
approve on the hrs estimated
Developed (development start the work)
in progress
Ready for test
Tester ok / ready for prod
move it to Pre-prod
released - in prod

## Eficode_report
1 | Good domain knowledge | 1 | Work prioritization ○ New features and manual testing heavily prioritized ○ Doing tasks at hand, continuous improvement activities aren’t really encouraged
2 | Good team collaboration and trust | 2 | No end-to-end process ○ First analysis ○ Then development ○ Then testing ○ Then UAT ○ Then wait until production ○ People handovers between flow
3 | ○ People trust each other | 3 | Unidentifiable software development method ○ VPS4IT is not a software development method ○ Some good practices still applied, like daily hurdle and the board to visualize to current state
4 | ○ Open communication also with management | 4 | Teamplace as requirement management tool ○ No data collection ○ No visualization - physical board to track CR statuses | JIRA is suggessted
5 | Some scripts exist ○ Daily build of static content ○ Daily update of SAP content and publish | 5 | Version control ○ SVN used, Git could be an approach for the future ○ MEGA has it’s own version control ○ Basic usage of branching is in use ○ All code isn’t in version control ○ A great possibility to have all code in the same repository | VC
|  | 6 | Separate CI does not exist Build operation (generation) takes hours ○ Instability issues ○ Debugging requires going to servers | Build
| No reporting ○ No details in test cases ○ Reporting gives value for the testing activities Multiple levels of manual testing ○ Dev, Test, UAT ○ Partially redundant |  | No test automation ● Some manual testing ○ 30 cases in teamplace ○ Test cases can be forgotten in CRs | Testing
| Application architecture ○ Both VGMS and VEAR are built around MEGA ○ Monolith deployments |  | No monitoring ○ HCL monitors servers ○ HCL offers application monitoring accessible by everyone Difficult to identify bottlenecks without data ○ Performance problems but no clear root cause | Monitoring - Infra tool
| Communication is mostly based on talking ○ OK for a small team |  | Slow releases ○ Release cycle about 3 months ○ Downtime for MEGA while importing ○ Deadline driven ○ CRs spend a long time in “Ready for prod” Ability to deploy every CR separately ○ Technically frequent deployments are possible | Release Process
Order the following services from DRS ○ Jenkins CI server ○ SonarQube