## XE_BPM_Roadmap
Phase 1 | Phase 2 | Phase 3
● CI / Jenkins server | ● Evaluate and take Git into use | ● Increase coverage for automated acceptance
● SonarQube | ● Define a workflow process | testing
● Take linters and other appropriate plugins into use | ● Definition of Done | ● Release notes
● Automate daily checkup of latest build state | ● Evaluate test automation frameworks | ● Remove UAT from the release process
● Evaluate and take Jira into use | ● Create automated test cases
● Move to Kanban
● Enable monitoring/tracking of services

## XE BPM DevOps Plan
XE BPM DevOps Plan
Instruction: Mark with an X in the time line when the deadline is set for each deliverable
[9 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | june |  |  | july |  |  |  | august |  |  |  |  | september |  |  |  | october |  |  |  | november |  |  |  |  | december |  |  |  | january/18 |  |  |  |  | february/18 |  |  |  | march/18 |  |  |  | april/18
[9 empty] | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
ID | X,X Milestones | Resp. | Status | Base | % spent | Base | % compl. | Corrective actions | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | CI / Jenkins server |  |  | 100% | 0% | 100% | 0%
1.1 | Raise request to have Jenkins for the team |  |  |  | 0% | 100% | 0%
1.2 | Take up training on Jenkins / self learning |  |  |  | 0% | 100% | 0%
1.1 | Define how XE BPM can work in a CI mode |  |  | 100% | 0% | 100% | 0%
1.2 | Configure Builds to have CI enabled build |  |  | 100% | 0% | 100% | 0%
1.3 | Enabling Jenkins to execute the manual tasks as much possible |  |  | 100% | 0% | 100% | 0%
2 | SonarQube |  |  | 100% | 0% | 100% | 0%
2.1 | Introducing Sonarqube |  |  | 100% | 0% | 100% | 0%
2.2 | Create rules for every new functionality |  |  | 100% | 0% | 100% | 0%
2.3 | Training on Sonarqube & Train the team
2.4 | Writing the unit testcase for critical code / transactions / frequently faced issues
2.5 | Integrate with CI tool like Jenkins |  |  |  | 0% | 100% | 0%
3 | Take linters and other appropriate plugins into use |  |  | 100% | 0% | 100% | 0%
3.1 | Analyse Code linter tool |  |  | 100% | 0% | 100% | 0%
3.2 | Research by the developers |  |  | 100% | 0% | 100% | 0%
3.3 | Check whether its open source/ license. Can be integreated with Jenkins
3.4 | Handover of the findings to the entire team |  |  | 100% | 0% | 100% | 0%
3.5 | Training the entire team |  |  | 100% | 0% | 100% | 0%
4 | Automate daily checkup of latest build state |  |  | 100% | 0% | 100% | 0%
4.1 | Automate the daily checkup task
4.2 | Modify the existing (Build )script to check the build status & share the log thru email to the team |  |  | 100% | 0% | 100% | 0%
5 | Evaluate and take Jira into use |  |  | 100% | 0% | 100% | 0%
5.1 | Take up JIRA training |  |  | 100% | 0% | 100% | 0%
5.2 | Analyse & Migrate from Teamplace to JIRA |  |  | 100% | 0% | 100% | 0%
5.3 | Team to follow Jira dashboad |  |  | 100% | 0% | 100% | 0%
5.4 | Introduce Daily stand up meetings for better colloboration |  |  | 100% | 0% | 100% | 0%
5.5 | Work on tasks / resource estimates & share the report
6 | Move to Kanban |  |  | 100% | 0% | 100% | 0%
6.1 | Discuss & finalize on Kanban : software delivery process |  |  | 100% | 0% | 100% | 0%
6.2 | Training on Kanban ways of working to take tasks quickly under development and release features when they become ready |  |  | 100% | 0% | 100% | 0%
6.3 |  |  |  | 100% | 0% | 100% | 0%
7 | Enable monitoring/tracking of services |  |  | 100% | 0% | 100% | 0%
7.1 | To evaluate the performance issue, raise access request to check the server logs |  |  | 100% | 0% | 100% | 0%
7.2 | How is the alert system configured, Does that cover |  |  | 100% | 0% | 100% | 0%
7.3
8 | Migration to GIT |  |  | 100% | 0% | 100% | 0%
8.1 |  |  |  | 100% | 0% | 100% | 0%
8.2 |  |  |  | 100% | 0% | 100% | 0%
8.3 |  |  |  | 100% | 0% | 100% | 0%
Note on B22: https://pypi.python.org/pypi/html-linter/