## NAMS DevOps Plan
NAMS DevOps Plan
Instruction: Mark with an X in the time line when the deadline is set for each deliverable
[9 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | june |  |  | july |  |  |  | august |  |  |  |  | september |  |  |  | october |  |  |  | november |  |  |  |  | december |  |  |  | january/18 |  |  |  |  | february/18 |  |  |  | march/18 |  |  |  | april/18
[9 empty] | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
ID | X,X Milestones | Resp. | Status | Base | % spent | Base | % compl. | Corrective actions | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Collaboration tool: evaluation and incorporation | Fabio |  | 100% | 0% | 100% | 0% | [40 empty] | x | x
1.1 | Decide which tool will be used (Slack) - used by VGT | Lead |  | 100% | 0% | 100% | 0% | [40 empty] | x
1.2 | Configure it for the team | Fabio |  | 100% | 0% | 100% | 0% | [41 empty] | x
1.3 | Demonstrate to the team how and why to use it | Fabio |  | 100% | 0% | 100% | 0% | [41 empty] | x
1.4 | Assume it as a standard tool to be used in all team comunications | Lead |  | 100% | 0% | 100% | 0% | [41 empty] | x
2 | Continuous Integration (CI) | Fabio/Kostas/Seilor |  | 100% | 0% | 100% | 0% | [41 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x
2.1 | Configure Builds to have CI build |  |  | 100% | 0% | 100% | 0% | [41 empty] | x
2.2 | Define how NAMS can work in a CI mode |  |  | 100% | 0% | 100% | 0% | [41 empty] | x
2.3 | Configuration must be automated when possible |  |  | 100% | 0% | 100% | 0% | [42 empty] | x | x | x | x | x | x | x | x | x | x | x | x
2.4 | Add SonarQube analisys |  |  | 100% | 0% | 100% | 0% | [42 empty] | x
3 | Robot Framework Implementation | Marlon |  | 100% | 0% | 100% | 0% | [40 empty] | x
3.1 | Create first smoke test |  |  | 100% | 0% | 100% | 0%
3.2 | Train more people to create tests |  |  | 100% | 0% | 100% | 0%
3.3 | Run it after deploymnets (recurrent task) |  |  | 100% | 0% | 100% | 0%
3.4 |  |  |  | 100% | 0% | 100% | 0%
4 | Braching and Merging | Fabio/Dewes |  | 100% | 0% | 100% | 0% | [40 empty] | x | x | x | x
4.1 | Evaluate the current model |  |  | 100% | 0% | 100% | 0% | [40 empty] | x
4.2 | Check the need and will to use git repos |  |  | 100% | 0% | 100% | 0% | [40 empty] | x
4.3 | Restructure what is needed |  |  | 100% | 0% | 100% | 0% | [40 empty] | x | x | x | x
4.4 |  |  |  | 100% | 0% | 100% | 0%
5 | General items |  |  | 100% | 0% | 100% | 0% | [40 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x
5.1 | Find someone from HCL to answer questions about the infrastructure |  |  | 100% | 0% | 100% | 0%
5.2 | Cloud: How, When, Where? |  |  | 100% | 0% | 100% | 0%
5.3 | Define what is "a Release" -> New model |  |  | 100% | 0% | 100% | 0%
5.4 | Windows Docker images investigation |  |  | 100% | 0% | 100% | 0% | [40 empty] | x
5.5 | Answer questions about Leadership | Annete |  | 100% | 0% | 100% | 0% | [40 empty] | x
6 | Continuous deployment |  |  | 100% | 0% | 100% | 0% | [53 empty] | x | x | x | x | x | x | x | x
6.1 | Prepare the CD standard |  |  | 100% | 0% | 100% | 0%
6.4 | Commit/Deploy/Test |  |  | 100% | 0% | 100% | 0%