## PROMPT (hidden)
DevOps Pilot Team: PROMPT (Eficode - Final report)
1 | Define mission | Select a timespan and work together to define a clear mission for PROMPT.
2 | Evaluate acceptance test framework | Evaluate the current test automation framework. Test cases and test report should be clear enough for business people to read and comprehend.
3 | Automated acceptance tests | Work together as a team to implement automated acceptance tests. Start with critical business flows. Reuse the current automated tests and HP Quality Center cases to build a core for automated acceptance tests. Abandon HP Quality Center. To unify versioning, make sure acceptance tests are in the same Git repository with code.
4 | Increase coverage of unit tests | Testing algorithms and different configuration combinations is not feasible in acceptance tests. Increase unit test level to cover all functions with important business logic in the application. Start using SonarQube to systematically track unit test coverage
5 | Definition of Done | Remove ready for testing column and start implementing testing along with code. When defining subtasks for a story, define also subtasks for unit and acceptance test implementation. Define and document Definition of Done so that it includes also test creation
6 | Git workflow | Define and document a proper Git branching strategy to support new Definition of Done and proper workflow. Start working together as development and testing in feature branches until the feature and both unit and acceptance tests are implemented and only then merge feature to master. Apply a code review process to merging into master
7 | Continuous integration plan | Trigger unit tests, build and deployment to test environment on every merge to master. Evolve the process later by triggering, for example, smoke tests for each push to test branches as well. Trigger automatic acceptance tests on every deployment to verify quality of new and existing features.
8 | Evaluate current environments | Evaluate whether all environments are needed.Take into account whether some environments could be removed while utilizing the CI-pipeline efficiently and business side would test from one QA-environment.
9 | Evaluate DB needs | Evaluate the current DB usage, take into account all used environments and future development plans. Study whether you could have an archive DB in use.
10 | Implement DB changes | Based on the previous step implement the changes that help the Team to perform its tasks from development to production. End users shouldn’t see a behaviour change caused by this change.
11 | Propose new release process | Whenever new EPICs are completed and tests pass in test environment, deploy to QA and let business know you’re ready for release any time they want. Make acceptance test results available for everyone
12 | Componentization plan | Establish a common understanding of individually deployable components in PROMPT. Make sure no components are both services and clients
13 | Componentization execution | Conduct componentization. Refactor PROMPT into separately deployable components
14 | Transition into OpenShift | Put components into Docker containers and deploy them to OpenShift when it’s officially production ready
15 | Build container monitoring | Start monitoring your containers and take end-to-end product responsibility. Use a modern container monitoring tool, for example, Prometheus.

## Roadmap
Phase 1 | Phase 2 | Phase 3
● Define mission | ● Evaluate DB needs | ● Transition into OpenShift
● Evaluate acceptance test framework | ● Implement DB changes | ● Build container monitoring
● Automated acceptance tests | ● Propose new release process
● Increase coverage of unit tests | ● Componentization plan
● Definition of Done | ● Componentization execution
● Git workflow
● Continuous integration plan
● Evaluate current environments

## PROMPT_DevOps Plan
PROMPT DevOps Plan
Instruction: Mark with an X in the time line when the deadline is set for each deliverable
[9 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | june |  |  | july |  |  |  | august |  |  |  |  | september |  |  |  | october |  |  |  | november |  |  |  |  | december |  |  |  | january/18 |  |  |  |  | february/18 |  |  |  | march/18 |  |  |  | april/18
[9 empty] | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w | w
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
ID | X,X Milestones | Resp. | Status | Base | % spent | Base | % compl. | Corrective actions | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Define the mission |  |  | 100% | 0% | 100% | 0%
1.1 | Identify needs from business | Prompt / Business |  | 100% | 0% | 100% | 0%
1.2 | Identify expectations from the team | Prompt / Business |  | 100% | 0% | 100% | 0%
1.3 | Form mission in one sentence | Prompt / Business |  | 100% | 0% | 100% | 0%
2 | Evaluate current environments |  |  | 100% | 0% | 100% | 0%
2.1 | Research on the environment is done. Optimise the current env. | Prompt / HCL |  | 100% | 0% | 100% | 0%
2.2 | Order sandbox & Test environment | DRS |  | 100% | 0% | 100% | 0%
2.3 | Trying out sandbox environment Creating env. in cloud | DRS / Prompt / HCL |  |  | 0% | 100% | 0%
3 | Evaluate acceptance test framework |  |  | 100% | 0% | 100% | 0%
3.1 | Robot framework - yes or no decision | Prompt |  | 100% | 0% | 100% | 0%
3.2 | Research by the developers | Prompt / DRS |  | 100% | 0% | 100% | 0%
3.3 | Checking the license of the tool | DRS
3.4 | Handover of the findings to the entire team | Prompt |  | 100% | 0% | 100% | 0%
3.5 | Training (about Robot framework) | DRS |  | 100% | 0% | 100% | 0%
4 | Automated acceptance tests - Robot Framework |  |  | 100% | 0% | 100% | 0%
4.1 | Training about good practices about DevOps | DRS
4.2 | Identify core flows / Decompose to simple elements | Prompt / Buz |  | 100% | 0% | 100% | 0%
4.3 | Plan migration of current tests | Prompt |  | 100% | 0% | 100% | 0%
4.4 | Migration of current tests | Prompt |  | 100% | 0% | 100% | 0%
4.5 | Implementation of new use cases | Prompt |  | 100% | 0% | 100% | 0%
4.6 | Investigate the possibility of CQ to JIRA | DRS
4.7 | Identify Performance test tool & define good approach in PT (Gatalien) | DRS
Yet to review the below items
5 | Core unit testing |  |  | 100% | 0% | 100% | 0%
5.1 | Introducing Sonarqube |  |  | 100% | 0% | 100% | 0%
5.2 | Create rules for every new functionality |  |  | 100% | 0% | 100% | 0%
5.3 | Training on Sonarqube & Train the team |  |  | 100% | 0% | 100% | 0%
5.4 | Writing the unit testcase for critical code / transactions / frequently faced issues |  |  | 100% | 0% | 100% | 0%
5.5 | Integrate with CI tool like Jenkins
6 | Definition of Done |  |  | 100% | 0% | 100% | 0%
6.1 | Checkilist followed to conclude on DOD |  |  | 100% | 0% | 100% | 0%
6.2 | How the status are captured, any tool used to confirm the end of that particular cycle |  |  | 100% | 0% | 100% | 0%
6.3 | Any tool used to share the DoD like Confluence tool - located in centralised place |  |  | 100% | 0% | 100% | 0%
7 | Git workflow |  |  | 100% | 0% | 100% | 0%
7.1 | Evaluate the current model |  |  | 100% | 0% | 100% | 0%
7.2 | Restructure what is needed |  |  | 100% | 0% | 100% | 0%
7.3 | Code review Gerrit in place
8 | Continuous integration plan |  |  | 100% | 0% | 100% | 0%
8.1 | Configure Builds to have CI build |  |  | 100% | 0% | 100% | 0%
8.2 | Define how PROMPT can work in a CI mode |  |  | 100% | 0% | 100% | 0%
8.3 | Configuration must be automated as much possible with Maven:Build, Sonaqube:Codequality |  |  | 100% | 0% | 100% | 0%
Note on D22: Check & decide on the dates